## Project Overview
Tower Lead AI Classifier — Client Proposal
Project Overview
An AI-assisted triage layer for your tower-lead pipeline. Discovery jobs (FCC, FAA,
ArcGIS, OpenStreetMap, CellMapper) generate a large pool of candidate leads. Today a
person reviews each one by hand to decide what is a real tower and what is not — only
~20% has been reviewed so far.
This project trains a machine-learning classifier on your already-reviewed leads and uses
it to score every remaining lead with a "tower likelihood." Your review queue is then sorted
by that score, so the most-likely towers surface first and obvious non-towers drop to the
bottom — dramatically speeding up the keep / discard decision while keeping a human in control.
Investment Summary
Total project price | 1080
Pricing model | Fixed price
Estimated timeline | ~4 weeks
What's Included
• Data audit to identify the reviewed leads and confirm the keep/discard labels.
• A trained classifier over your existing lead fields (source, structure type, licensee,
location, and lead density) — runs locally, no per-record AI fees.
• Model accuracy report (so you can trust the scores before relying on them).
• Automated scoring of all unreviewed leads, refreshed as new leads arrive.
• Review screen upgrade: leads ranked by tower likelihood, with a one-click
"Not a tower" button that also teaches the model over time.
• End-to-end testing and a short hand-over note.
What's Not Included
• Fully automatic deletion of leads (kept human-in-the-loop by design).
• New discovery data sources or pipeline re-architecture.
• Satellite-image vision analysis (available as a future add-on).
Assumptions
• The reviewed ~20% yields enough confirmed non-tower examples to train on. If the
data proves too sparse, we first ship the "Not a tower" tool to collect labels, then
train (handled as a separate change order).
• Runs inside the existing application and database; hosting is the client's.

## How the AI Learns
How the AI Learns
This is supervised machine learning: the model learns from the keep / discard decisions your team has already made, then applies that judgement to the leads no one has reviewed yet. No data leaves your system, and there are no per-lead AI fees.
Step | What happens
1. Learn from your decisions | We start from the leads your team has already reviewed (~20%). Each one a person confirmed as a real tower, or marked as not a tower, becomes a labeled example — the "answer key" the model learns from.
2. Turn each lead into signals | For every lead we extract the characteristics that hint at whether it's a tower: the data source, structure type, whether it carries an FCC license / callsign, the licensee or carrier, the location, and how isolated vs. clustered it is among nearby leads (real towers tend to stand alone; rooftop points cluster together).
3. Train the model | A proven structured machine-learning model studies these labeled examples and learns which combinations of signals predict a real tower. It stays transparent — we can report which signals matter most, rather than relying on a black box.
4. Test before we trust it | We hold back a portion of your reviewed leads that the model never sees during training, then measure how accurately it predicts them. You receive an accuracy report so you know exactly how reliable the scores are before relying on them.
5. Score the rest | The trained model gives each of the unreviewed ~80% a "tower likelihood" from 0 to 100%.
6. Rank your review queue | Leads are sorted by that score, so the most-likely towers rise to the top and obvious non-towers sink — your team reviews the best candidates first and skips the junk.
7. It improves over time | Every "promote" or "Not a tower" click adds a fresh labeled example. Periodic retraining makes the model sharper as your reviewed data grows.

## Milestones
Milestones & Payment Schedule
Milestone | Deliverables | Price
A. Data foundation & model | Data audit + label confirmation; database fields & migration; feature engineering (incl. lead-density signals); trained classifier with an accuracy report. | 630
B. Automation & review tooling | Automated scoring job for all unreviewed leads; review screen ranked by tower likelihood, score filter, and one-click "Not a tower" action that retrains the model. | 330
C. Testing & handover | End-to-end validation against real leads (spot-checked on satellite imagery) and a short admin/hand-over note. | 120
Total
Fixed price of $1,080. Milestones may be invoiced on completion. Estimated ~4 weeks.